YONC PROJECT SYSTEM

# Graph-Based Project Management System

Graph core, runtime boundaries, data model, operations, completion semantics, and delivery forecast

System specification v1.0 — 28 Aug 2026  |  Audience: Architecture, product, data, agent integration

Lossless structured synthesis of the shared design conversation

Shared design conversation

# Information preservation note

This specification preserves the full conceptual progression in the source discussion and reconciles it with Yonc_Graph_Project_System_Spec_v0.1.md: general Graph Engineering, the existing Yonc repository baseline, the proposed graph architecture, later scope reductions, and the accepted completion/timeline decisions. Earlier ideas that were superseded remain documented as history rather than being silently merged into the final model.

System definition: A human–agent collaborative project graph that stores project truth, structure, time, state, and resource references; supports reasoning and graph operations; and projects the same source into Canvas, Timeline, Portfolio, Mobile, and optional Notion views.

# 1. Graph Engineering context

Graph Engineering is the explicit design of nodes, edges, shared state, routing, branches, loops, gates, parallelism, verification, permissions, recovery, and stop conditions. It is not merely drawing a graph and it does not replace agent loops.

| Concept | Meaning in an agent/project system |
| --- | --- |
| Node | Agent, tool, function, validator, human approval, project item, or promoted artifact. |
| Edge | The explicit relationship or next path: contains, depends_on, blocks, produces, validates, and others. |
| State | Shared project and runtime facts carried between operations. |
| Branch | Conditional path selected from current state or validation result. |
| Loop | Repeated work/check/fix cycle inside a node or agent. |
| Gate | Condition or approval required before transition. |
| Parallel | Independent nodes or agents that may proceed concurrently. |

Graph definitions may be expressed in JSON, YAML, code-based builder APIs, or database rows. The format is secondary; the essential structure is nodes + edges + conditions + runtime/state behavior. For a Hermes-style multi-agent platform, graph logic belongs in the orchestration layer while each agent can keep its own internal plan/act/check loop.

Prompt → Context → Harness → Loop → Graph → Agent System

Graph = coordination among loops/agents/tools
Loop  = local plan → act → check → fix

# 2. Existing Yonc baseline from the source discussion

The source discussion reported that the repository already contains dashboard/state/flow foundations rather than a blank agent shell. These notes are preserved as the design baseline and should be revalidated against the current code during implementation.

- dashboard.py, current_state.json, flow_runs logs, cron/state/config readers, and Timeliner-related logic already exist.

- README describes a system for INTP + ADHD that decomposes abstract goals to executable action.

- Existing WBS: L1 Goal → L2 Deliverable → L3 Work Package → L4 Activity → Atomic Refinement; Project and Exploratory OKR use different decomposition patterns.

- task_reader.py reportedly builds recursive records with id, title, parent_id, depth, and children. This is already a hierarchy tree even if Notion displays bullets.

- dashboard.py reportedly groups tasks by Mode, Task Type, and Theme, answering ‘what should I see today?’ but not ‘what does the entire project look like?’

- state_evaluator.py reportedly derives lifecycle from node properties, and main flow already calls the evaluator while older flow-l1/l2/l3 paths are legacy wrappers.

- Timeliner rank/scope already affects ordering and flow. Timeliner should therefore remain a time/pressure engine rather than being replaced by the new graph manager.

| Existing-state sequence reported in source | Interpretation |
| --- | --- |
| RAW → STRUCTURED → SCOPED → SEQUENCED | A node acquires structure, scope, and ordering. |
| EXPANDING → HUMAN_REVIEW | The node is split and the AI proposal awaits human approval. |
| PHASING_WAIT → ACTIONABLE_PENDING | Timing/phase or Mode/Task Type details remain unresolved. |
| READY → COMPLETED | The node becomes executable and later complete. |

The later product discussion introduced a different lifecycle vocabulary (raw, clarified, structured, split needed, split proposed, approved, ready, doing, review, done) plus stage/status separation. A final one-to-one migration mapping was not resolved and remains an implementation task.

# 3. System boundary and source of truth

- Notion is one UI/projection. The source of truth is the repository-backed graph store, initially compatible with an upgraded current_state.json or equivalent graph JSON.

- All views read the same graph. Canvas, Timeline, Mobile, Portfolio, Notion, and external agents must not maintain divergent task truth.

- The system owns project truth, structure, lifecycle, deadlines, estimates, dependencies, resources/artifacts, warnings, and history.

- The project system does not own general Agent Work Queue or Human Review Queue orchestration. That was explicitly removed from scope.

- External agents may read the graph, propose work, attach outputs, or request permitted updates; user completion authority remains final.

Project Graph scope
= Project truth + structure + timeline + visualization + operations
≠ universal agent scheduler / workload queue

# 4. Logical architecture

| Component | Responsibility |
| --- | --- |
| Graph Store | Authoritative graph ID/version, committed nodes/edges, resource references, derived values, and view-independent facts. |
| Graph Builder | Transforms a fuzzy goal or approved Split Session proposal into candidate nodes and edges. |
| Graph Evaluator | Checks graph health: actionability, missing outputs, orphan nodes, dependency cycles, deadline conflicts, and other constraints. |
| Graph Operations | Only supported mutation path: create/link/split/commit/move/set deadline/mark done/cancel/supersede/attach resource; produces event history and undo. |
| Graph Runtime | Evaluates state transitions, route/edge conditions, readiness, derived values, and recomputation. General agent scheduling is outside this product's MVP scope. |
| Timeliner | Owns temporal rank, deadlines, estimated span/finish, delivery pace, pressure, and time-related constraints. |
| View Projector | Projects the same graph into Canvas, Timeline, Portfolio, Mobile/Focus, and optional Notion views. |
| Event History | Records operations needed for review, recovery, sync, and undo. Detailed changed_by metadata is useful but was downgraded from product core. |

User / Agent
      ↓
Graph Builder / Split Session
      ↓ candidate
Draft Proposal Graph
      ↓ user Commit
Graph Operations → Graph Store → Evaluator / Runtime / Timeliner
                                  ↓
                      Canvas | Timeline | Mobile | Notion

# 5. Graph data model

## 5.1 Top-level graph

graph
├─ id
├─ version
├─ nodes[]
├─ edges[]
├─ derived_state / runtime data
└─ view_state references (stored separately from graph facts)

## 5.2 Node core

| Field group | Fields / semantics |
| --- | --- |
| Identity | id, title, node_type, wbs_level, project/theme |
| Classification | tags, Mode, Task Type, priority, phase where applicable |
| Lifecycle | stage and status as separate concepts; completion remains an explicit status fact |
| Time | planned/rough start, deadline, estimated_effort, estimated_span, estimated_finish, optional observed_work_time, temporal_pressure |
| Execution definition | start cue, inputs, done_when/output definition; often stored inside an Action rather than as more graph nodes |
| Resources | resource references; important resources may be promoted to Artifact nodes |
| Metadata | confidence, optional change/audit details, generated/human review markers, other extensible properties |

Core node types begin with project/goal, deliverable/module, work_package, and action. Artifact, Resource, and Agent may become graph nodes only when their relationships justify it. Simple files and links remain references.

## 5.3 Edge taxonomy

| Category | Edge types | Notes |
| --- | --- | --- |
| Structural | contains | Carries required=true/false for progress and closure calculations. |
| Logical | depends_on, blocks, blocked_by, related_to, validates | Makes ordering, blocking, verification, and cross-linking explicit. |
| Execution | executed_by, uses | Connects work to agents/tools/resources when needed; assignment does not imply the graph system schedules a global queue. |
| Output | produces, used_by | Links work to artifact/resource references or promoted artifact nodes. |
| History | superseded_by | Preserves replacement history without deleting the prior node. |

The accepted minimal edge set for an initial graph upgrade was contains, dependency/depends_on, and blocks. The broader taxonomy is retained for system evolution.

## 5.4 Resource and artifact model

- Artifact is first an Artifact Reference / pathway, not necessarily an uploaded file or a graph node.

- Supported reference styles may include local://, github://, notion://, https://, s3://, drive://, and conversation://.

- Promote a resource to an Artifact Node when it has versions, is shared by many tasks, produces other artifacts, or needs explicit graph relationships.

- The graph needs to know where an output lives; it does not need to become a full file manager.

# 6. Draft, committed graph, operations, and view state

- Draft/Proposal Graph is separate from Committed Graph. AI-proposed nodes and edges do not become project truth until user Commit.

- Every change is a graph operation rather than an arbitrary JSON edit. Examples: propose_split, approve/commit_split, link_dependency, set_deadline, move_schedule, mark_done, cancel, supersede, attach_resource.

- Committing a split emits CREATE_NODE and CREATE_EDGE operations; the event history enables review and undo.

- View state (expanded/collapsed, selected scope, filters, zoom/pan, manual layout) is separate from graph facts and may vary by view.

- UI placement must not be hard-coded into task truth. A future UI can project the same graph differently.

# 7. Lifecycle, status, and completion authority

## 7.1 Stage versus status

Stage describes the lifecycle phase; status/runtime state describes what is happening now. A node may be stage=execution and status=blocked, or stage=planning and status=proposed. The exact normalized enums must be reconciled with the existing state_evaluator vocabulary.

## 7.2 Completion rules

- DONE has one final rule: the user explicitly says/marks Done. This applies to Action, Module, and Parent nodes.

- Agents may prepare work, produce artifacts, submit, or propose completion, but they do not unilaterally set DONE by default.

- Children 4/4 complete does not auto-complete the Parent. It is a calculated fact only; the user may add validation or declare the scope complete.

- The previously proposed READY_TO_CLOSE / closure-suggestion flow was superseded by the simpler explicit-user-Done rule. A non-blocking suggestion may exist, but it is not a status transition requirement.

- DONE does not require a reason because that would add friction.

- CANCELLED requires reason. SUPERSEDED requires reason and may link superseded_by to the replacement node.

## 7.3 Progress calculation

progress = completed estimated effort of required Actions
           / total estimated effort of required Actions

Fallback when estimates are absent:
completed required children / total required children

- Progress and status are independent. A node may be user-marked DONE while calculated progress remains 87% because some planned actions became unnecessary.

- Only required=true children contribute to default progress. Optional work does not prevent 100%.

- Task-count progress is a fallback because a 15-hour action must not equal a 20-minute action.

# 8. Time, effort, forecast, and recomputation

| Field | Meaning |
| --- | --- |
| estimated_effort | Relative task size in hour-equivalent; user value > AI suggestion > Task Type default. |
| observed_work_time | Optional passively observed active-session time; never claimed as actual labor time. |
| observed_delivery_pace | Completed estimated workload per calendar window; accepted first-version historical signal. |
| estimated_span | Likely natural-calendar range; not a fixed plan. |
| estimated_finish | Dynamic forecast range derived from workload, delivery pace, dependency, current load, and deadline constraints. |
| deadline | Hard anchor the project must not cross; separate from estimated finish. |
| temporal_pressure | Timeliner-derived pressure shown as Canvas glow and explained in Timeline. |

Graph mutations must propagate. Adding an action, changing effort, completing work, changing a dependency, or moving a deadline recomputes parent workload, estimated span/finish, deadline gap, temporal pressure, and Canvas/Timeline projections.

- Use the recent 4–8 weeks of user-marked DONE estimated effort to calculate typical delivery pace.

- Use a typical/median pace and preserve variability; show ranges rather than false precision.

- Task-type-specific pace and estimate-confidence visualization remain future enhancements.

- No mandatory timer and no completion-time Q&A.

# 9. Graph health and constraints

- Child beyond parent deadline

- B depends on A but is planned before A

- Circular dependency

- Orphan node

- Large node that remains unsplit / fails the Actionability Contract

- Action missing an output or done_when definition

- Blocked too long

- Agent output stalled or submitted without a resource reference (future integration)

UI behavior is intentionally quiet: normally show one small warning icon in the card corner; clicking reveals reason and affected nodes. Health checks advise and expose structural issues rather than making hidden decisions for the user.

# 10. Agent and tool interface

The Project Graph acts as a shared coordination substrate. Main Orchestrator and external agents may query it, open a Split Session, propose execution, link outputs, and submit permitted operations. A Coding, Research, BIM, or Reviewer agent can keep its own internal loop while the outer graph defines relationships and gates.

project.list / project.get_graph / project.get_node
project.get_children / project.get_dependencies / project.get_resources
split.start / split.get_context / split.propose / split.revise
split.get_current_proposal / split.commit
node.mark_done / node.cancel / node.supersede
node.set_deadline / node.add_resource

These names are an interface direction, not a frozen API. Final permissions must ensure agents cannot silently rewrite committed project truth or completion status.

## 10.1 End-to-end processing flow

- User creates or imports a project and the initial graph node exists.

- User opens a Split Session; user and AI discuss and agree on decomposition.

- User commits the split; graph operations create children and edges.

- Estimated effort is assigned from user input, AI suggestion, or Task Type default.

- Derived state recalculates; Canvas re-renders and Timeline forecast updates.

- User may place modules roughly on the Timeline; this changes temporal intent, not graph identity.

- The user works in real life or external agents produce artifacts; resource references attach to the relevant nodes.

- User explicitly marks DONE; Observed Delivery Pace updates and future forecasts become progressively more realistic.

# 11. MVP and phased evolution

| Phase | Scope |
| --- | --- |
| MVP | Graph source of truth; core nodes; contains/depends_on/blocks; operations/history; collaborative split; user-only Done; resources; Canvas and Timeline projections; delivery-pace forecast. |
| Next | Graph health expansion, promoted artifact nodes, richer external-agent read/propose interfaces, uncertainty ranges, task-type delivery pace. |
| Later | Conditional multi-agent graph runtime, richer checkpointer/scheduler integration, dynamic graph generation, advanced validation and permissions. |

# 12. Decision ledger

| Status | Decision |
| --- | --- |
| Accepted | Graph Engineering means nodes + edges + rules + state transitions + runtime reasoning; it is not merely graph storage. |
| Accepted | JSON/repository graph is source of truth; Notion and all other UIs are projections. |
| Accepted | Graph Store, Builder, Evaluator, Operations, Runtime, Timeliner, View Projector, and Event History form the logical architecture. |
| Accepted | Draft proposals stay separate until Commit; view state stays separate from graph facts; operations/history support undo. |
| Accepted | User alone defines DONE; required/optional supports weighted progress; Cancelled/Superseded require reason. |
| Accepted | Resource references are lightweight pathways; promote to Artifact Node only when relationships require it. |
| Deferred | Exact lifecycle migration mapping, estimate confidence UI, task-type-specific pace, detailed change-source metadata. |
| Out of scope | Owning general agent work queues and human review queues; arbitrary autonomous scheduling across agents. |

Reference coverage: the v0.1 specification’s product definition/scope, source of truth, node/edge models, actionability, operations, completion, estimation, derived state, resources, external-agent interface, architecture, processing flow, non-violation rules, and MVP are preserved in Sections 1–12. Canvas/Timeline interaction detail is intentionally routed to Document 01; the full collaborative split workflow is routed to Document 03.

# Source references

- Shared ChatGPT design conversation

- Yonc Graph Project System Specification v0.1

- Yonc Agent repository