YONC PROJECT SYSTEM

# Collaborative Task Decomposition

Split Session workflow, Actionability Contract, proposal lifecycle, and commit semantics

Workflow specification v1.0 — 28 Aug 2026  |  Audience: Product, agent design, UX, graph operations

Lossless structured synthesis of the shared design conversation

Shared design conversation

# Information preservation note

This document isolates every substantive task-decomposition decision from the source conversation and Yonc_Graph_Project_System_Spec_v0.1.md: the LineV2/WBS hierarchy, OKR awareness, the rejection of black-box auto-splitting, the full Split Session workflow, stop conditions, bounded exploration, external-agent/MCP entry points, proposal/commit separation, completion authority, and the accepted estimate defaults.

Non-negotiable rule: Task decomposition is a negotiated human–AI workflow. The agent proposes and revises; the user decides whether the graph is actionable enough and explicitly commits the split.

# 1. Purpose and non-goals

- Turn a fuzzy Goal, Objective, Key Result, Deliverable, Module, or Work Package into a small set of actionable graph nodes.

- Reduce decision load at the point of execution without exploding the graph into meaningless micro-steps.

- Preserve the parent intent, output expectations, dependencies, required/optional status, estimates, tags, and resource context.

- Keep AI-proposed decomposition outside committed project truth until user Commit.

- Do not act as a black-box automatic splitter and do not pretend uncertain work has a fully known step sequence.

# 2. Structural model: Lines, OKR, WBS, and project scope

| Level / concept | Role |
| --- | --- |
| Line / Programme / Objective | Long-running direction or major outcome; may contain Key Results or major projects. |
| L1 Goal | High-level desired state; usually too large to execute directly. |
| L2 Deliverable / Module | Substantial project-shaped result; may appear as a Portfolio project card. |
| L3 Work Package | Coherent cluster of work that produces part of a Deliverable. |
| L4 Action | Directly startable work that satisfies the Actionability Contract. |
| Atomic Refinement | Lightweight execution definition inside an Action; not automatically another graph layer. |

The existing Yonc design reportedly supports both Project and Exploratory OKR decomposition. The new Split capability must therefore be OKR-aware: Objective → Key Results → graph work, while retaining the WBS lineage used by LineV2. WBS level alone never proves that a node is actionable.

- Any node may be chosen as current Project Scope, making decomposition relative to the user's current scale.

- A WBS L2 Module can be managed as a project without changing its underlying graph identity.

- Inbox/Capture remains a valid pre-decomposition layer: an idea may be captured before the user knows its project or WBS level.

# 3. Actionability Contract

Action definition: An Action can be started without another round of ‘how do I do this?’ planning and has an observable result that lets the user decide whether it is complete.

| Criterion | Test |
| --- | --- |
| Startable | If shown now, does the user know the first physical/digital step? |
| Observable Done | Is there a concrete output, state change, or result that makes completion discussable? |
| Single Intent | Is it one main action rather than research + compare + write + revise hidden inside one label? |
| Decision Load | Does execution still require a major planning/design decision? If so, split or clarify further. |
| Bounded Effort | Can it advance in one or a small number of reasonable work sessions? This is a soft rule, not a strict two-hour threshold. |

Decision Load is the most important ADHD-oriented test. A short-looking task may still be bad if it hides many choices. Conversely, a 2.5-hour task can be a good Action if its input, intended output, and method are already clear.

Bad:  ‘Write Methodology’
Better: ‘Using prototype-test.md, turn the existing experiment steps into a 400–600 word Methodology 2.3 draft.’

## 3.1 Atomic Refinement inside an Action

Stop expanding the graph at the Action by default. Store the final activation details inside the node.

Action: Write Graph Core design spec
Start: Open graph-core.md
Inputs: Previous architecture discussion
Done when:
  - Node model documented
  - Edge model documented
  - One architecture diagram exists

This preserves a manageable Canvas while still lowering activation energy.

## 3.2 Bounded exploration

Unknown work such as debugging or research cannot always be honestly decomposed into deterministic steps. Convert it into a bounded exploration whose next action and output are known even though the answer is not.

Investigate intermittent crash for 45 minutes
Output:
  - Reproduction steps
  - Three likely causes
  - Next experiment

The key distinction is: the answer may be uncertain; the next action must not be.

# 4. Split Session workflow

- Open a Split Session from a selected parent node.

- Load parent goal, lineage, existing children, dependencies, resources, tags, lifecycle, deadline, estimates, and relevant constraints.

- Agent identifies ambiguity and proposes decomposition version 1 with rationale, outputs, dependencies, estimates, and required/optional flags.

- User responds conversationally: merge, remove, rename, keep coarse, change output, change sequence, or split further.

- Agent revises the proposal and keeps a visible current proposal alongside the chat.

- Agent evaluates the proposed leaves against the Actionability Contract and explains why it believes each is actionable.

- User chooses Continue splitting, Modify, or Commit. Consensus is practical agreement, not an autonomous AI verdict.

- Commit emits graph operations that create nodes/edges and records history for review and undo.

OPEN SESSION → Proposal v1 → User feedback → Proposal v2 → …
→ Actionability check → User Commit → CREATE_NODE / CREATE_EDGE operations

# 5. Entry points and reusable service

The Canvas sub-chat is one entry point, not the implementation boundary. The same workflow must be callable from desktop, mobile, an external chat, another agent, or an MCP/tool interface.

| Entry point | Behavior |
| --- | --- |
| Canvas | Hover right edge/right corner about 0.8–1.0 seconds to reveal +; click opens compact split sub-chat and proposal panel. |
| Mobile | Long-press or select a node, then choose Split; use a full-screen conversational flow rather than graph dragging. |
| External agent/chat | Agent identifies graph/node, starts a session, discusses with the user, then calls commit only after explicit approval. |
| MCP/tool API | Programmatic access to session context, proposals, revision, validation, and commit. |

split.start(parent_node_id)
split.get_context(session_id)
split.propose(session_id, proposal)
split.discuss(session_id, user_feedback)
split.revise(session_id)
split.get_proposal(session_id)
split.commit(session_id)

# 6. Split Session UI

| Area | Required behavior |
| --- | --- |
| Session header | Parent node title, lineage, lifecycle, deadline, and why splitting was invoked. |
| Conversation | AI rationale and user feedback in a compact chat; retain context without turning the Canvas into a chat wall. |
| Current proposal | Live tree/graph preview with outputs, required/optional flags, dependencies, estimates, and validation indicators. |
| Proposal status | Clearly draft; semi-transparent/partial border/dashed edges; never visually equal to committed graph. |
| Actions | Continue discussion, Split deeper, Modify, Discard, Commit Split. |

The plus affordance means enter Graph Construction. It is not a quick-add todo button. The user must always be able to see the current proposal before commit.

# 7. Proposal and session data

| Object | Minimum fields |
| --- | --- |
| SplitSession | id, parent_node_id, state, context_snapshot/version, created_at, current_proposal_id |
| Proposal | id, version, rationale, proposed_nodes, proposed_edges, actionability_results, warnings |
| Proposed node | title, node_type/WBS, output/done_when, estimate, tags, required/optional, uncertainty, resource inputs |
| Proposed edge | type, source, target, required flag, rationale/condition where needed |
| Commit result | operation IDs, created node/edge IDs, graph version, warnings, undo reference |

Suggested session states: OPEN, PROPOSAL_DRAFT, PENDING_USER_REVIEW, REVISING, APPROVED, COMMITTED, DISCARDED. The exact enum names were not frozen in the source; the essential rule is that proposed and committed states remain distinct.

# 8. Estimate behavior during decomposition

- Each Action receives estimated_effort. Source precedence is user value, AI suggestion, then Task Type default when blank.

- Accepted configurable default examples: Read 30m, Search 45m, Research 60m, Write 90m, Design 120m, Build 120m, Discussion 30m.

- AI may offer a range (for example 45–90 minutes) with an editable working estimate.

- The estimate describes task size; it is not a calendar promise.

- Do not ask the user to report actual effort on completion. No mandatory timer or completion Q&A.

- User-marked DONE effort later contributes to Observed Delivery Pace and Elastic Timeline forecasting.

# 9. Commit, graph operations, history, and undo

- Commit validates that the parent graph version still matches the session context or explicitly resolves conflicts.

- Create all proposed child nodes and structural edges as a coherent operation batch; add dependency/output edges in the same batch where appropriate.

- Preserve required/optional semantics on contains edges.

- Record the committed proposal version and graph operation IDs so the change can be reviewed and undone.

- A split revision that is not committed does not alter project truth.

- Graph health re-runs after commit. New work triggers workload, estimate, deadline-gap, and temporal-pressure recomputation.

# 10. Completion and agent participation

- Agents may inspect the graph, volunteer for agent-capable work, prepare artifacts, and submit results, subject to permission.

- The project system stores task structure/state and artifact references; general agent work/human review queues remain out of scope.

- Agent completion is a proposal/submission. DONE occurs only when the user explicitly says/marks Done.

- Children all complete does not auto-complete the Parent. Calculated progress and status are separate.

- A simple resource may be linked as a pathway; a highly connected result may be promoted to an Artifact Node.

# 11. Worked examples

## 11.1 Product module

Parent: Develop Project Management Module

Proposal:
1. Define project data model
2. Build Project API (depends on 1)
3. Build Project Map UI (depends on 1)
4. Integrate graph operations (depends on 2 + 3)
5. Test project workflow (depends on 4)

The proposal remains draft while discussed. After Commit, steps 2 and 3 become parallel-ready when step 1 is user-marked Done; the graph can then unlock step 4.

## 11.2 Research gap

Too large: Research Gap
Suggested decomposition:
- Search papers
- Extract theory
- Extract results
- Extract limitations
- Build gap matrix
- Define gap

Dependency idea:
Search → parallel extraction → Gap matrix → Gap definition

## 11.3 Actionability refinement

Not actionable: Research Graph Engineering
Actionable: Find five agent-graph architecture implementations and record each implementation's node, edge, and runtime approach in graph-notes.md.

# 12. Graph-health checks related to splitting

- Node is too large or repeatedly fails Actionability criteria.

- Leaf lacks a clear output or done_when definition.

- Proposal creates orphan nodes, circular dependencies, or an impossible order.

- Child estimate/deadline makes the parent forecast exceed its deadline.

- Proposal duplicates existing children or artifacts.

- Proposal decomposes an uncertain problem into false certainty instead of bounded exploration.

- Graph expansion creates too many trivial nodes; recommend Atomic Refinement inside an Action.

# 13. Decision ledger

| Status | Decision |
| --- | --- |
| Accepted | Decomposition is a Collaborative Split Session with multiple proposal/revision rounds and explicit user Commit. |
| Accepted | Split capability is service-level and reusable from Canvas, Mobile, external chat/agent, and MCP/tool interfaces. |
| Accepted | Actionability Contract uses Startable, Observable Done, Single Intent, Decision Load, and Bounded Effort; duration alone is insufficient. |
| Accepted | Graph stops at Action by default; Atomic Refinement provides start/inputs/done_when without producing graph clutter. |
| Accepted | Bounded exploration handles genuinely uncertain work without inventing fake deterministic steps. |
| Accepted | Draft/proposal is separate from committed reality; graph operations/history support undo. |
| Accepted | Task Type default is used when no estimate is supplied; no actual-effort Q&A or mandatory timer. |
| Rejected | AI black-box auto-decomposition and WBS-level-only stop rules. |
| Out of scope | Project system ownership of general Agent Work Queue or Human Review Queue. |

# 14. MVP acceptance criteria

- A user can start a Split Session from a node and see parent context plus a visible draft proposal.

- The agent supports iterative feedback and proposal versioning; no graph mutation occurs before Commit.

- Every proposed leaf is evaluated against all Actionability criteria and includes output/done_when.

- Bounded exploration is available for uncertain work.

- Commit creates operation history, required/optional contains edges, dependencies, estimates, and an undo reference.

- External tool/agent entry points call the same workflow and cannot bypass explicit commit/permission rules.

- Post-commit graph health and Elastic Timeline derived values recompute.

- User-only Done authority remains intact.

Reference coverage: v0.1 Sections 7–10, 56–61, and the decomposition-related parts of Sections 58–63 are represented in Sections 1–14. Repetition was consolidated, while workflow states, control meanings, examples, APIs, commit semantics, and non-negotiable rules were retained.

# Source references

- Shared ChatGPT design conversation

- Yonc Graph Project System Specification v0.1

- Yonc Agent repository